## At a glance
Project Status values | Meaning | (optional) Project Status code
Need to send application | we have a lead, but we haven't mailed them an application yet | 1
Waiting on application | we are waiting for homeowner to send us an application | 2
Application incomplete | we are waiting for some documents from homeowner | 3
Need to do initial inspection | we have application, but Greg/Alice need to do assessment | 4
Need to submit in CDS | we need to submit application in CDS | 5
Waiting on city approval | we are waiting for the city to approve the project | 6
Need to assign HC | we have to find a house captain willing to do work | 7
Need to assign date | we have to set the date of the project | 8
Need supplies or support | we have to organize supplies ahead of the project date, and/or we need volunteers for the project | 9
Waiting on work day | everything is ready, we are waiting for the work to happen | 10
Need to follow up | work day is over, but need to print photos, update website, send thank yous, update future SOW | 11
Done | everything is done; this project is over | 12
(We could use the status code to help the pivot table list the pipeline in order.)
Row Labels
Application incomplete
RT 103
RT 104
Need to send application
RT 106
Need to submit to CDS
RT 102
Waiting on application
RT 105
Waiting on city approval
RT 101
Grand Total

## Project Pipeline
Project Name | Homeowner Name | Project Status | Current updates | Application sent date | Application Date | Document 1 completion date | Document 2 completion Date | Submitted to CDS date | Approved by CDS date | Current Scope of Work
RT 101 | Kunal Marwaha | Waiting on city approval | need to find a painter | 2018-11-01 | 2018-12-02 | 2018-12-08 | 2018-12-04 | 2018-12-05 |  | This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.
RT 102 | Elizabeth Athena | Need to submit to CDS | contact flooring company | 2018-11-03 | 2018-12-02 | 2018-12-04 | 2018-12-15 |  |  | This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.
RT 103 | Another Name | Application incomplete |  | 2018-11-03 | 2018-12-02 | 2018-12-05
RT 104 | George Reskin | Application incomplete |  | 2018-11-05 | 2018-12-02 |  |  |  |  | This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.
RT 105 | Bob Doe | Waiting on application |  | 2018-11-11 | [5 empty] | This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.
RT 106 | Jesus Garcia | Need to send application | [7 empty] | This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.This is a really long text string.